## Table with Risks and Measures
Number | Group | Risk | Risk Description | Likelyhood | Severity | Likelyhood times Severity | Accept | Reduce | Transfer | Avoid | Detail Action | Strategy Decision What | When
1 | Goal | Unclear question | The topic description is to vague or contains to many goals | 2 | 2 | 4 |  | X |  |  | Define SMART goals | Reduce: In the research section smart goals have been setup | 2026-10-24
2 | Goal | Unclear goals | The goals are not clearly defined or can not be measured | 2 | 3 | 6 |  | X |  |  | Describe which goals are part of scope | Reduce: The introduction describes which parts of the initial project description are part of this document | 2026-10-24
3 | Time and Organisation | Insufficient expertise | Not knowing required tools or programming languages | 4 | 2 | 8 | X |  |  |  | Learning is part of the journey but additional time is to planed | Accept : Nothing done | 2026-10-24
4 | Time and Organisation | Undererstimated time/effort | Some tasks take more time than initially expected | 4 | 4 | 16 |  | X |  |  | Phases and Milestones are set up as progress checks | Reduce: Phases and Milestones are set up as progress checks | 2026-10-24
5 | Time and Organisation | Other study projects | Other classes demand more attention, less time for project | 3 | 3 | 9 | X |  |  |  | Use minimum time for Projects/classes | Accept : Nothing done | 2026-10-24
6 | Time and Organisation | Work projects | Other projects at work demand urgent attention, less time for project | 4 | 3 | 12 |  | X |  |  | Reduction of risk due to starting early, defining blockers for study work | Reduce: Discussed availability with other team, added blockers in work calendar, work account invited to meeting Series (Jour Fixe), study Account: Set blockers on weekend, researched with ChatGPT for optimal or minimal study plan | 2026-10-24
7 | Time and Organisation | Procrastination | Tasks are pushed back | 3 | 2 | 6 |  | X |  |  | Start early | Reduce: Work on he project started 14.09.2026, first meeting with expert in same week | 2026-10-24
8 | Human Resources | Unavailability of main project staff, e.g. due to illness | One or multiple project staff are not available | 5 | 4 | 20 |  | X |  |  | Happened before start, Provide contact of partner working at BFH, Document in case it hapens | Reduce: Contact of partner provided in teams, and added to Miro board | 2026-10-24
9 | Human Resources | Unavailability of advisor, e.g. due to illness, accident etc. | The advisor is not available | 3 | 3 | 9 |  |  | X |  | Advisor to define emergency replacement | Transfer: Asked for contact, confirmed to be Jürgen Vogel | 2026-10-24
10 | Tech and Infrastructure | Software Version/Library/Dependency | Missmatch in Versions, new library versions break the code | 4 | 3 | 12 | X |  |  |  | Run the code multiple times, have tetcases e.g. unittests | Accept : Nothing done | 2026-10-24
11 | Tech and Infrastructure | Hardware is damaged | The Laptops or other material is damaged and needs repairs or replacement | 2 | 4 | 8 |  | X |  |  | Second Laptop, Code on Github/Miro/Teams/Outlook | Second Laptop is available at home, The Latex document is a Github project, documentation is on miro. Work laptop can also be used for most tasks, but has no Latex installed | 2026-10-24
12 | Data and research | Data related | Bias in data, not enough data | 4 | 4 | 16 | X |  |  |  | No preparation to be planned | Accept : Nothing done | 2026-10-24
13 | Data and research | Not reproducable work | The work provided can not be reproduced | 1 | 5 | 5 |  | X |  |  | Document bigger Steps, Upload Versions on Github of document, in Miro use Kanban to document tasks | Reduce: Github project for Latex document | 2026-10-24
14 | Ethical and Legal | Plagiarism or wrong citation | Unallowed or undeclared usage of sources | 2 | 5 | 10 |  | X |  |  | Use Citation, Bibliography | Reduce: Jabref used as GUI for biblliography, Biber used for build | 2026-10-24
15 | Ethical and Legal | Copyright | Used literature or materials which are restricted | 1 | 5 | 5 | X |  |  |  | Declare sources in bibliography, in case of post sources only use public documents | Accept : Nothing done | 2026-10-24
16 | Communication and Cooperation | Bad communication with stakeholder or advisor | Advisor or stakeholders are not heared. Their inputs are ignored | 1 | 4 | 4 |  | X |  |  | Weekly Advisor Meetings, Jour Fixe | Reduce: Jour fixe setup | 2026-10-24
17 | Communication and Cooperation | insufficient exchange with external partners | External partners do not react, are delayed or communication towards them is late or poor | 3 | 5 | 15 |  | X |  |  | Stakeholders in Scrum Team | Reduce: Keep exchange chanells also when changing team | 2026-10-24
18 | Force Majeure | Unforseen familiar crisis | Unecpected crisis in family | 2 | 5 | 10 | X |  |  |  | To be documented in miro calendar case it happens | Accept : Nothing done | 2026-10-24
19 | Force Majeure | General force majeure | Events which can not be influenced are very rare and very disruptive | 1 | 5 | 5 | X |  |  |  | To be documented in miro calendar case it happens | Accept : Nothing done | 2026-10-24
20 | Unknown Process | The required management process is unknown | The resopnsible parties need to be found first | 4 | 2 | 8 |  | X |  |  | Project 1 and 2 established much of the required steps, however it is still likely that something new can pop up | Reduce: Still important to handle them as soon as they apear | 2026-10-24
21 | Communication and Cooperation | Required resources are not available when needed, or responsibilities are unclear | Resources within team or outside team are not available | 3 | 4 | 12 |  | X |  |  | Setup calls early, search external resources always before starting work blocks | Reduce: Search external before doing your part | 2026-10-24
22 | Organisational | Changes pushed by organisation | The Swiss Post defined new directions which affect the research | 3 | 4 | 12 | X |  |  |  | Change is constant, discussion of teams required | Accept: Exchange with teams | 2026-10-24
23 | Data and research | Insufficient scientific contribution | This research does not add sufficient scientific value | 1 | 5 | 5 |  | X |  |  | Providing continous feedback and having weekly call are done to find missing contributions early | Reduce: Part of Jour fixe | 2026-10-24

## Table with Risks_Projekt2
Number | Group | Risk | Risk Description | Likelyhood | Severity | Likelyhood times Severity | Accept | Reduce | Transfer | Avoid | Detail Action | Strategy Decision What | When | Checkup When | Checkup Action or OK
1 | Goal | Unclear question | The topic description is to vague or contains to many goals | 2 | 2 | 4 |  | X |  |  | Define SMART goals | In the research section smart goals have been setup | 2099-10-23
2 | Goal | Unclear goals | The goals are not clearly defined or can not be measured | 2 | 3 | 6 |  | X |  |  | Describe which goals are part of scope | The introduction describes which parts of the initial project description are part of this document
3 | Time and Organisation | Insufficient expertise | Not knowing required tools or programming languages | 4 | 2 | 8 | X |  |  |  | Risk is accepted, learning is wanted effect | Accept : Nothing done | 2025-10-23
4 | Time and Organisation | Undererstimated time/effort | Some tasks take more time than initially expected | 4 | 3 | 12 | X |  |  |  | Document end of tasks in Miro Calendar, Reevaluate after project | Accept : Nothing done | 2025-10-23
5 | Time and Organisation | Other study projects | Other classes demand more attention, less time for project | 3 | 3 | 9 | X |  |  |  | Use minimum time for Projects/classes | Accept : Nothing done | 2025-10-23
6 | Time and Organisation | Work projects | Other projects at work demand urgent attention, less time for project | 4 | 3 | 12 |  | X |  |  | Reduction of risk due to starting early, defining blockers for study work | Added blockers in Work calendar, Work Account invited to meeting Series (Jour Fixe), Study Account: Set Blockers on Weekend, Researched with ChatGPT for optimal or minimal study plan | 2025-10-10
7 | Time and Organisation | Procrastination | Tasks are pushed back | 3 | 2 | 6 |  | X |  |  | Start early | Work on he project started 25.09.2025, when attending data quality meeting at AWS, beeing part of AWS Modernisation initiative | 2025-10-17
8 | Human Resources | Unavailability of main project staff, e.g. due to illness | One or multiple project staff are not available | 4 | 4 | 16 |  | X |  |  | Provide contact of partner working at BFH, Document in case it hapens | Contact of partner provided in teams, and added to Miro board | 2025-10-23
9 | Human Resources | Unavailability of advisor, e.g. due to illness, accident etc. | The advisor is not available | 3 | 4 | 12 |  |  | X |  | Advisor to define emergency replacement | Asked for Contact, Confirmed to be Jürgen Vogel | 2025-10-23
10 | Tech and Infrastructure | Software Version/Library/Dependency | Missmatch in Versions, new library versions break the code | 4 | 3 | 12 | X |  |  |  | Run the code multiple times, have tetcases e.g. unittests | Accept : Nothing done | 2025-10-23
11 | Tech and Infrastructure | Hardware is damaged | The Laptops or other material is damaged and needs repairs or replacement | 2 | 5 | 10 |  | X |  |  | Second Laptop, Code on Github/Miro/Teams/Outlook | Second Laptop is available at home, The Latex document is a Github project, documentation is on miro. Work Laptop can also be used for most tasks, but has no Latex installed | 23.10.205
12 | Data and research | Data related | Bias in data, not enough data | 4 | 3 | 12 | X |  |  |  | No preparation to be planned | Accept : Nothing done | 2025-10-23
13 | Data and research | Not reproducable work | The work provided can not be reproduced | 2 | 5 | 10 |  | X |  |  | Document bigger Steps, Upload Versions on Github of document, in Miro use Kanban to document tasks | Github project for Latex Document | 2025-10-10
14 | Ethical and Legal | Plagiarism or wrong citation | Unallowed or undeclared usage of sources | 2 | 5 | 10 |  | X |  |  | Use Citation, Bibliography | Jabref used as GUI for Biblliography, Biber used for build | 2025-10-17
15 | Ethical and Legal | Copyright | Used literature or materials which are restricted | 1 | 5 | 5 | X |  |  |  | Declare sources in bibliography, in case of post sources only use public documents | Accept : Nothing done | 2025-10-10
16 | Communication and Cooperation | Bad communication with stakeholder or advisor | Advisor or stakeholders are not heared. Their inputs are ignored | 2 | 4 | 8 |  | X |  |  | Weekly Advisor Meetings, Jour Fixe | Jour Fixe Setup | 2025-09-26
17 | Communication and Cooperation | insufficient exchange with external partners | External partners do not react, are delayed or communication towards them is late or poor | 1 | 5 | 5 |  | X |  |  | Stakeholders in Scrum Team | Keep exchange chanells also when changing team | 2025-09-26
18 | Force Majeure | Unforseen familiar crisis | Unecpected crisis in family | 2 | 5 | 10 | X |  |  |  | To be documented in miro calendar case it happens | Accept : Nothing done | 2025-10-23
19 | Force Majeure | General force majeure | Events which can not be influenced are very rare and very disruptive | 1 | 5 | 5 | X |  |  |  | To be documented in miro calendar case it happens | Accept : Nothing done | 2025-10-23
20 | Unknown Process | The required management process regarding contracts is not known, steps need to be found out | Accepting sources need to be found first | 5 | 3 | 15 |  | X | [7 empty] | Project 1 and 2 established much of the required steps | Accept: As third project most steps are repeated | 2026-10-24

## Graphical Overview
Likelyhood | Risk Matrix | Severity
|  | Insignificant | Minor | Moderate | Major | Severe
| Almost Certain |  |  |  | 8
| Likely |  | 3, 20 | 6, 10 | 4, 12
| Possible |  | 7 | 5, 9 | 21, 22 | 17
| Unlikely |  | 1 | 2 | 11 | 14, 18
| Rare |  |  |  | 16 | 13, 15, 19, 23
[7 empty] | Number | Likelyhood | Severity | Likelyhood times Severity | Number | Likelyhood | Severity
[7 empty] | 1 | 2 | 2 | 4 | 1 | 2 | 2 | 4 | Gleich
[7 empty] | 2 | 2 | 3 | 6 | 2 | 2 | 3 | 6 | Gleich
[7 empty] | 3 | 4 | 2 | 8 | 3 | 4 | 2 | 8 | Gleich
[7 empty] | 4 | 4 | 4 | 16 | 4 | 4 | 3 | 12 | Nicht Gleich
[7 empty] | 5 | 3 | 3 | 9 | 5 | 3 | 3 | 9 | Gleich
[7 empty] | 6 | 4 | 3 | 12 | 6 | 4 | 3 | 12 | Gleich
[7 empty] | 7 | 3 | 2 | 6 | 7 | 3 | 2 | 6 | Gleich
[7 empty] | 8 | 5 | 4 | 20 | 8 | 4 | 4 | 16 | Nicht Gleich
[7 empty] | 9 | 3 | 3 | 9 | 9 | 3 | 4 | 12 | Nicht Gleich
[7 empty] | 10 | 4 | 3 | 12 | 10 | 4 | 3 | 12 | Gleich
[7 empty] | 11 | 2 | 4 | 8 | 11 | 2 | 5 | 10 | Nicht Gleich
[7 empty] | 12 | 4 | 4 | 16 | 12 | 4 | 3 | 12 | Nicht Gleich
[7 empty] | 13 | 1 | 5 | 5 | 13 | 2 | 5 | 10 | Nicht Gleich
[7 empty] | 14 | 2 | 5 | 10 | 14 | 2 | 5 | 10 | Gleich
[7 empty] | 15 | 1 | 5 | 5 | 15 | 1 | 5 | 5 | Gleich
[7 empty] | 16 | 1 | 4 | 4 | 16 | 2 | 4 | 8 | Nicht Gleich
[7 empty] | 17 | 3 | 5 | 15 | 17 | 1 | 5 | 5 | Nicht Gleich
[7 empty] | 18 | 2 | 5 | 10 | 18 | 2 | 5 | 10 | Gleich
[7 empty] | 19 | 1 | 5 | 5 | 19 | 1 | 5 | 5 | Gleich
[7 empty] | 20 | 4 | 2 | 8 | 20 | 5 | 3 | 15 | Nicht Gleich
[7 empty] | 21 | 3 | 4 | 12 |  |  |  | 0 | Nicht Gleich
[7 empty] | 22 | 3 | 4 | 12 |  |  |  | 0 | Nicht Gleich
[7 empty] | 23 | 1 | 5 | 5 |  |  |  | 0 | Nicht Gleich

## Graphical Overview (2)
[7 empty] | Number | Likelyhood | Severity
Likelyhood | Risk Matrix | Severity |  |  |  |  | 1 | 2 | 2
|  | Insignificant | Minor | Moderate | Major | Severe | 2 | 2 | 3
| Almost Certain | 15, 17, 19 | 11, 14 |  |  |  | 3 | 4 | 2
| Likely | 21 | 16 | 9 | 8 |  | 4 | 4 | 3
| Possible |  |  | 5 | 4, 6, 10, 12 |  | 5 | 3 | 3
| Unlikely |  | 1 | 2, 7 | 3 |  | 6 | 4 | 3
| Rare | [5 empty] | 7 | 3 | 2
[7 empty] | 8 | 4 | 4
[7 empty] | 9 | 3 | 4
[7 empty] | 10 | 4 | 3
[7 empty] | 11 | 2 | 5
[7 empty] | 12 | 4 | 3
[7 empty] | 13 | 2 | 5
[7 empty] | 14 | 2 | 5
[7 empty] | 15 | 1 | 5
[7 empty] | 16 | 2 | 4
[7 empty] | 17 | 1 | 5
[7 empty] | 18 | 2 | 5
[7 empty] | 19 | 2 | 5
[7 empty] | 20 | 1 | 5
[7 empty] | 21 | 1 | 4

## RiskEval
Number | Group | Risk | Likelyhood | Severity
1 | Goal | Unclear question | 2 | 2
2 | Goal | Unclear goals | 2 | 3
3 | Time and Organisation | Insufficient expertise | 4 | 2
4 | Time and Organisation | Undererstimated time/effort | 4 | 3
5 | Time and Organisation | Other study projects | 3 | 3
6 | Time and Organisation | Work projects | 4 | 3
7 | Time and Organisation | Procrastination | 3 | 2
8 | Human Resources | Unavailability of main project staff, e.g. due to illness | 4 | 4
9 | Human Resources | Unavailability of advisor, e.g. due to illness, accident etc. | 3 | 4
10 | Tech and Infrastructure | Software Version/Library/Dependency | 4 | 3
11 | Tech and Infrastructure | Hardware is damaged | 2 | 5
12 | Data and research | Data related | 4 | 3
13 | Data and research | Not reproducable work | 2 | 5
14 | Ethical and Legal | Plagiarism or wrong citation | 2 | 5
15 | Ethical and Legal | Copyright | 1 | 5
16 | Communication and Cooperation | Bad communication with stakeholder or advisor | 2 | 4
17 | Communication and Cooperation | insufficient exchange with external partners | 1 | 5
18 | Force Majeure | Unforseen familiar crisis | 2 | 5
19 | Force Majeure | General Force majeure | 2 | 5

## RiskTreatment
Number | Risk | Risk Description | Treatment | Treatment Description
1 | Unclear question | The topic description is to vague or contains to many goals | Reduce | Define SMART goals
2 | Unclear goals | The goals are not clearly defined or can not be measured | Reduce | Describe which goals are part of scope
3 | Insufficient expertise | Not knowing required tools or programming languages | Accept | Document after risk occured
4 | Undererstimated time/effort | Some tasks take more time than initially expected | Accept | Document end of tasks in Miro Calendar, Reevaluate after project
5 | Other study projects | Other classes demand more attention, less time for project | Accept | Use minimum time for Projects/classes
6 | Work projects | Other projects at work demand urgent attention, less time for project | Reduce | Reduction of risk due to starting early, defining blockers for study work
7 | Procrastination | Tasks are pushed back | Reduce | Start early
8 | Unavailability of main project staff | One or multiple project staff are not available | Accept | Document in case it hapens
9 | Unavailability of advisor | The advisor is not available | Transfer | Advisor to define emergency replacement
10 | Software Version/Library/Dependency | Missmatch in Versions, new library versions break the code | Accept | Run the code multiple times, have tetcases e.g. unittests
11 | Hardware is damaged | The Laptops or other material is damaged and needs repairs or replacement | Reduce | Second Laptop, Code on Github/Miro/Teams/Outlook
12 | Data related | Bias in data, not enough data | Accept
13 | Not reproducable work | The work provided can not be reproduced | Reduce | Document Steps, Upload Versions on Github
14 | Plagiarism or wrong citation | Unallowed or undeclared usage of sources | Reduce | Use Citation, Bibliography
15 | Copyright | Used literature or materials which are restricted | Accept
16 | Bad communication with stakeholder or advisor | Advisor or stakeholders are not heared. Their inputs are ignored | Reduce | Weekly Advisor Meetings
17 | insufficient exchange with external partners | External partners do not react, are delayed or communication towards them is late or poor | Reduce | Stakeholders in Scrum Team
18 | Unforseen familiar crisis | Unecpected crisis in family | Accept | To be documented in miro calendar case it happens
19 | General Force majeure | Events which can not be influenced are very rare and very disruptive | Accept | To be documented in miro calendar case it happens

## RiskWhatWhen
Number | Risk | Strategy Decision What | When
1 | Unclear question | In the research section smart goals have been setup | 2099-10-23
2 | Unclear goals | The introduction describes which parts of the initial project description are part of this document
3 | Insufficient expertise | Accept : Nothing done | 2025-10-23
4 | Undererstimated time/effort | Accept : Nothing done | 2025-10-23
5 | Other study projects | Accept : Nothing done | 2025-10-23
6 | Work projects | Added blockers in Work calendar, Work Account invited to meeting Series (Jour Fixe), Study Account: Set Blockers on Weekend, Researched with ChatGPT for optimal or minimal study plan | 2025-10-10
7 | Procrastination | Work on he project started 25.09.2025, when attending data quality meeting at AWS, beeing part of AWS Modernisation initiative | 2025-10-17
8 | Unavailability of main project staff, e.g. due to illness | Contact of partner provided in teams, and added to Miro board | 2025-10-23
9 | Unavailability of advisor, e.g. due to illness, accident etc. | Asked for Contact, Confirmed to be Jürgen Vogel | 2025-10-23
10 | Software Version/Library/Dependency | Accept : Nothing done | 2025-10-23
11 | Hardware is damaged | Second Laptop is available at home, The Latex document is a Github project, documentation is on miro. Work Laptop can also be used for most tasks, but has no Latex installed | 23.10.205
12 | Data related | Accept : Nothing done | 2025-10-23
13 | Not reproducable work | Github project for Latex Document | 2025-10-10
14 | Plagiarism or wrong citation | Jabref used as GUI for Biblliography, Biber used for build | 2025-10-17
15 | Copyright | Accept : Nothing done | 2025-10-10
16 | Bad communication with stakeholder or advisor | Jour Fixe Setup | 2025-09-26
17 | insufficient exchange with external partners | Keep exchange chanells also when changing team | 2025-09-26
18 | Unforseen familiar crisis | Accept : Nothing done | 2025-10-23
19 | General Force majeure | Accept : Nothing done | 2025-10-23

## CheckinOct
Number | Risk | Occured, Yes/No | Detail | Why | Measures taken | Measure date
1 | Unclear question | No |  | Measures taken
2 | Unclear goals | No |  | Team Members, PO in team
3 | Insufficient expertise | Yes | Latex usage to change document structure | Some parts of the used bfh template had to be changed, some were changed due to amendments with tables etc. added and needed fixes | used chatgpt for review and changes | 2026-07-24
4 | Undererstimated time/effort | Yes | Efforts for writing were not commitable before holiday | Took to much time in relation to needed cool down times | Moved writing partially to holiday | 2026-07-24
5 | Other study projects | Yes | No time invested | Focus on this project |  | 2026-07-24
6 | Work projects | No | In December much more work on the project was possible, no incidents | Full focus on new topics
7 | Procrastination | No |  | Now time to finish | Working hard during beach holiday | 2026-07-24
8 | Unavailability of main project staff, e.g. due to illness | No
9 | Unavailability of advisor, e.g. due to illness, accident etc. | No
10 | Software Version/Library/Dependency | No
11 | Hardware is damaged | No
12 | Data related | No
13 | Not reproducable work | No
14 | Plagiarism or wrong citation | No
15 | Copyright | No
16 | Bad communication with stakeholder or advisor | No
17 | insufficient exchange with external partners | No
18 | Unforseen familiar crisis | No
19 | General force majeure | No
20 | Unknown Process | Yes | Finally after a lot of back and forth the invoice was handled trough sending it via post mail | BFH could not sign the new Terms of Post | Next invoice to be sent by mail directly | 2026-07-01