## Tabelle1
Phase | Milestone | MS Date | Week Number
1 | 0 | 2026-09-14 | 38 | Start of Thesis
1 | 1 | 2026-10-18 | 42 | Use Case Defined
1 | None |  | 52 | End of Phase 1
2 | 2 | 2026-11-15 | 46 | Stakeholder meetings held
2 | 3 | 2026-11-29 | 48 | Error documentation by stakeholders started
2 | None | Irgendwann | #VALUE! | End of Phase 2
3 | 4 | 2026-12-13 | 50 | Development environment set, initial setup of tools
3 | 5 | 2027-01-24 | 3 | Data retrievable from source
3 | 6 | 2027-03-21 | 11 | MVP, has been setup
3 | None | Irgendwann | #VALUE! | End of Phase 3
4 | 7 | 2027-04-04 | 13 | MVP, presented to Swiss Post stakeholders
4 | 8 | 2027-04-18 | 15 | Outline, of second iteration defined
4 | None | Irgendwnn | #VALUE! | End of Phase 4
5 | 9 | 2027-05-16 | 19 | Data of different approaches compared
5 | None | Irgendwann | #VALUE! | End of Phase 5
6 | 10 | 2027-07-11 | 27 | Thesis document completed
6 | 11 | 2027-07-25 | 29 | Presentation ready
6 | None | 2027-08-22 | 33 | End of Phase 6
Formulas:
Week Number = ISOWEEKNUM([MS Date])