## Tabelle1
Major Risk Categories & Examples
Category | Risk | Description / Why it matters | Possible Mitigation
Data-related | Insufficient data / wrong data | You might not be able to obtain enough data, or the data doesn’t suit your research question. | Early check of data availability; backup data sources; pilot data collection
Data-related | Poor data quality / missing values / noise | Data may contain errors, missing or inconsistent entries, outliers, etc. | Data cleaning pipeline; robust methods; exploratory data analysis; sensitivity analyses
| Data leakage / target leakage | Information from the test set “leaks” into training resulting in over-optimistic models. | Strict train–test split; cross-validation protocols; careful feature engineering. See e.g. research on reproducibility and leakage arXiv
Data-related | Bias in data (sampling bias, measurement bias) | The data might systematically misrepresent some groups or features, harming generalizability. | Be aware of representativeness; use reweighting, stratification; discuss bias explicitly.
Data-related | Privacy / confidentiality / legal constraints | The data may include sensitive info and be subject to privacy laws (GDPR etc.). | Anonymize, use differential privacy methods, get ethics permission, restrict access.
Data-related | Data access / permission withdrawal | Data access might get revoked, or you lose API credentials, or permissions change. | Document agreements; have fallback datasets; negotiate access early.
Methodological / Modeling | Overfitting / underfitting | The model may be too complex (fitting noise) or too simple (not capturing signal). | Regularization, cross-validation, model selection.
Data-related | Model interpretability / explainability issues | Especially in “black box” models, you may not understand model decisions, which undermines trust. | Use interpretable models or post-hoc explanation techniques (LIME, SHAP).
| Inappropriate choice of metrics | The metric you optimize may not reflect real-world relevance. | Choose evaluation metrics aligned with the research question / stakeholder needs.
Data-related | Reproducibility issues | Others (or yourself later) may not be able to reproduce results due to missing code, random seeds, etc. | Release code/data, fix software versions, document pipeline.
Scope & Planning | Scope creep / changing goals | The project expands beyond what is feasible in the available time. | Define clear, bounded objectives; revisit scope periodically.
| Underestimation of time / effort | Some tasks (data cleaning, debugging) often take much more time than expected. | Time buffer, iterative schedule, milestones.
| Resource constraints (compute, memory) | Models may require more computing power, memory, GPU time than available. | Estimate computational resources ahead; use cloud or HPC if needed.
Technical / Infrastructure | Software / library dependencies / version conflicts | Upgrades or mismatches may break your code. | Use virtual environments, containerization (Docker), record versions.
| Hardware failures / data loss | Disk crashes, hardware errors, power outages. | Use backups (version control, cloud), regular commits.
Ethical / Legal / Societal | Ethical misuse / adversarial attacks | Models might be used in harmful ways, or manipulated. | Ethical review, adversarial robustness, disclaimers.
| Lack of consent / informed consent | If using human subjects or personal data, the subjects must consent. | Ethical approval, anonymization, IRB processes.
| Algorithmic fairness / discrimination | The model might perpetuate or amplify bias. | Fairness-aware methods, audits, fairness metrics.
Validation & Deployment | No real-world validation | The model might perform well in lab but fail in deployment. | Use hold-out test sets, pilot deployments, feedback loops.
| Concept drift / data shift | The data distribution may change over time, making the model obsolete. | Monitor performance over time; plan for retraining, adaptation.
Human / Organizational | Insufficient expertise | You may lack skills (statistics, ML, domain knowledge) required. | Seek supervision, take tutorials, collaborate.
| Communication / stakeholder mismatch | Misunderstanding the goals with supervisors or domain experts. | Frequent check-ins, written specifications.
| Motivation / burnout / time management | The workload may lead to fatigue or delays. | Break tasks, set realistic schedules, self-care.
Research & Publication | Negative or null results | You might find that there’s no strong signal or effect. | Be ready to present null findings; pre-register or justify.
| Publication / reproducibility pressure | Pressure to produce impressive results may lead to questionable practices. | Aim for methodological rigor, document all decision
🧩 Allgemeine Risiken einer Masterarbeit
1️⃣ Themenwahl & Zieldefinition
Risiko | Beschreibung | Beispiel | Mögliche Gegenmaßnahmen
Unklare oder zu breite Fragestellung | Das Thema ist zu vage oder umfasst zu viele Teilaspekte → keine klare Forschungsrichtung. | „Künstliche Intelligenz in der Medizin“ ohne Eingrenzung. | Früh mit Betreuer Zieldefinition abstimmen, Exposé schreiben, Scope klar eingrenzen.
Thema zu eng / kaum Quellen | Zu spezielles Thema erschwert Literaturrecherche oder Datensammlung. | Nur eine bestimmte Softwareversion als Forschungsgegenstand. | Literatur-Scoping-Review vor Projektstart; ggf. Thema leicht anpassen.
Themenänderung während der Arbeit | Änderungen im Projekt führen zu Verzögerungen. | Neue Methode scheint interessanter, Projekt wird umgeplant. | Änderungsmanagement etablieren, Betreuer informieren, neuen Zeitplan erstellen.
2️⃣ Zeitmanagement & Organisation
Risiko | Beschreibung | Beispiel | Gegenmaßnahmen
Zeitliche Fehleinschätzung | Einzelne Arbeitsschritte dauern deutlich länger als geplant. | Datenaufbereitung nimmt doppelt so viel Zeit wie erwartet. | Zeitpuffer einplanen (20–30 %), Gantt-Plan nutzen, wöchentliche Meilensteine.
Prokrastination / Motivationsabfall | Aufschieben oder Überforderung führt zu Zeitdruck am Ende. | Wochenlang kein Fortschritt, Abgabe in Gefahr. | Arbeitsplan mit kleinen Etappen; Betreuer-Check-ins; feste Schreibzeiten.
Abgabefristen & Bürokratie übersehen | Formale Fristen (Anmeldung, Abgabe, Verlängerung) werden übersehen. | Anmeldung zu spät eingereicht. | Terminplan mit Fristen erstellen, Erinnerungen setzen.
3️⃣ Personelle Risiken
Risiko | Beschreibung | Beispiel | Gegenmaßnahmen
Ausfall von Projektteilnehmern (z. B. Krankheit) | Teammitglied oder Studierender selbst fällt temporär oder dauerhaft aus. | Krankheit oder familiäre Verpflichtungen. | Früh Aufgaben verteilen, Backup-Person oder Ersatzplan haben; Betreuer informieren; ggf. Fristverlängerung beantragen.
Betreuer-Ausfall oder mangelnde Betreuung | Betreuer ist krank, wechselt Institution oder reagiert nicht. | Betreuer im Ausland, keine Rückmeldungen mehr. | Zweitbetreuer bestimmen; Kommunikationskanäle früh klären; regelmäßige Berichte senden.
Konflikte im Team (bei Gruppenarbeiten) | Unstimmigkeiten führen zu Spannungen, schlechter Zusammenarbeit. | Unterschiedliche Arbeitsstile oder Prioritäten. | Rollenverteilung dokumentieren, Teamregeln definieren, Konfliktgespräche moderieren.
4️⃣ Technische & Infrastruktur-Risiken
Risiko | Beschreibung | Beispiel | Gegenmaßnahmen
Hardwareausfall / Datenverlust | Rechnerdefekt, Festplattenfehler oder Stromausfall führen zu Verlust von Arbeit oder Daten. | Laptop kaputt, kein Backup. | Regelmäßige Backups (lokal + Cloud), Versionskontrolle (Git), USV bei sensibler Hardware.
Softwareprobleme / Versionskonflikte | Tools, Bibliotheken oder Updates führen zu Inkompatibilitäten. | Nach Update läuft Code nicht mehr. | Virtuelle Umgebungen, Docker-Container, Softwareversionen dokumentieren.
Zugriffsverlust auf Systeme oder Server | Rechte oder Passwörter gehen verloren; Accounts gesperrt. | Uni-Account läuft ab. | Frühzeitige Verlängerung, lokale Kopien wichtiger Daten.
Fehlende oder defekte Messgeräte | Bei experimentellen Arbeiten: Sensoren oder Geräte fallen aus. | Defekter Sensor im Labor. | Ersatzgeräte reservieren, Wartung einplanen, Laborpersonal früh einbeziehen.
5️⃣ Daten- & Forschungsrisiken
Risiko | Beschreibung | Beispiel | Gegenmaßnahmen
Daten nicht verfügbar / Zugriff verweigert | Externe Partner liefern keine Daten oder Kooperationsvertrag scheitert. | Firma zieht Datennutzung zurück. | Früh verbindliche Zusage einholen; alternative Datenquellen vorbereiten.
Datenqualität unzureichend | Fehlerhafte, unvollständige oder verrauschte Daten. | Messwerte fehlerhaft oder inkonsistent. | Datenbereinigung, Plausibilitätsprüfungen, Qualitätssicherung dokumentieren.
Fehlende Reproduzierbarkeit / Dokumentation | Arbeit kann später nicht nachvollzogen werden. | Keine Versionskontrolle, fehlende Protokolle. | Dokumentation parallel führen, Code kommentieren, README-Dateien erstellen.
Unzureichende Methodenauswahl | Gewählte Methoden passen nicht zur Forschungsfrage. | Falsche statistische Tests. | Früh mit Betreuer oder Methodenexperten abstimmen, ggf. Pilotstudie durchführen.
6️⃣ Ethische & rechtliche Risiken
Risiko | Beschreibung | Beispiel | Gegenmaßnahmen
Datenschutzverletzung / ethische Probleme | Personenbezogene Daten oder vertrauliche Informationen unsachgemäß behandelt. | Veröffentlichung sensibler Patientendaten. | Anonymisierung, DSGVO beachten, Ethikvotum einholen.
Plagiat / falsche Zitation | Unerlaubte Übernahme fremder Texte oder Ideen. | Copy-Paste aus Artikeln ohne Quellen. | Plagiatsprüfung, Zitationsregeln einhalten, Quellen dokumentieren.
Urheberrechtsverletzung | Nutzung von Bildern, Texten oder Code ohne Lizenz. | Grafiken aus Publikationen übernommen. | Creative Commons oder eigene Grafiken nutzen; Rechte prüfen.
Interessenskonflikt mit externen Partnern | Externe Auftraggeber verlangen Ergebnismanipulation oder Geheimhaltung. | Firma will negative Resultate nicht veröffentlicht sehen. | Vertragliche Klarheit, Transparenz mit Hochschule, Ethikleitlinien beachten.
7️⃣ Kommunikation & Zusammenarbeit
Risiko | Beschreibung | Beispiel | Gegenmaßnahmen
Schlechte Kommunikation mit Betreuer / Stakeholdern | Missverständnisse über Erwartungen oder Fortschritt. | Unterschiedliche Zielvorstellungen. | Regelmäßige Statusberichte, Protokolle, Feedback einholen.
Mangelnde Abstimmung mit Kooperationspartnern | Externe Partner antworten zu spät oder gar nicht. | Unternehmen reagiert nicht auf E-Mails. | Klare Ansprechpartner und Kommunikationsrhythmus definieren.
Fehlendes Feedback | Arbeit entwickelt sich in falsche Richtung. | Betreuer liest Entwurf erst kurz vor Abgabe. | Zwischenstände regelmäßig einreichen, Feedbacktermine früh fixieren.
8️⃣ Schreibprozess & Abgabe
Risiko | Beschreibung | Beispiel | Gegenmaßnahmen
Formatierungsprobleme / technische Fehler | LaTeX-Fehler, defekte Abbildungen, Verzeichnisse falsch. | Abbildungen nicht eingebunden. | Frühzeitig Formatvorlage einrichten, Testdruck durchführen.
Druck- oder Upload-Probleme | Datei zu groß, falsches Format, Serverausfall bei Upload. | Upload kurz vor Deadline scheitert. | Einen Tag vorher finalisieren, mehrere Backups.
Schreibblockaden / Überforderung am Ende | Zeitdruck, Angst, Stress → keine Produktivität. | Kurz vor Abgabe kein Fortschritt. | Schreibplan mit kleinen Zielen, regelmäßige Pausen, ggf. Unterstützung durch Schreibberatung.
9️⃣ Externe & Umweltfaktoren
Risiko | Beschreibung | Beispiel | Gegenmaßnahmen
Krankheit / Unfall / persönliche Belastung | Unerwartete gesundheitliche Ausfälle. | Grippe, Unfall, familiäre Krise. | Pufferzeit, Kommunikation mit Prüfungsamt, ggf. Verlängerungsantrag.
Pandemie / höhere Gewalt / Naturereignisse | Ereignisse außerhalb der Kontrolle stören den Zeitplan. | Laborzugang während Pandemie gesperrt. | Digitale Alternativen, Notfallplan, Online-Meetings.
Stromausfall / Internetprobleme | Technische Störungen verhindern Arbeit. | Kein Internetzugang während Online-Recherche. | Offline-Kopien wichtiger Quellen, lokale Backups, mobile Daten als Reserve.

## Tabelle2
Data-related | Poor data quality / missing values / noise | Data may contain errors, missing or inconsistent entries, outliers, etc.
Data-related | Bias in data (sampling bias, measurement bias) | The data might systematically misrepresent some groups or features, harming generalizability.
Data-related | Privacy / confidentiality / legal constraints | The data may include sensitive info and be subject to privacy laws (GDPR etc.).
Data-related | Data access / permission withdrawal | Data access might get revoked, or you lose API credentials, or permissions change.
Data-related | Model interpretability / explainability issues | Especially in “black box” models, you may not understand model decisions, which undermines trust.
Data-related | Reproducibility issues | Others (or yourself later) may not be able to reproduce results due to missing code, random seeds, etc.
Scope & Planning | Scope creep / changing goals | The project expands beyond what is feasible in the available time.
| Underestimation of time / effort | Some tasks (data cleaning, debugging) often take much more time than expected.
Technical / Infrastructure | Software / library dependencies / version conflicts | Upgrades or mismatches may break your code.
| Hardware failures / data loss | Disk crashes, hardware errors, power outages.
| Algorithmic fairness / discrimination | The model might perpetuate or amplify bias.
Validation & Deployment | No real-world validation | The model might perform well in lab but fail in deployment.
| Concept drift / data shift | The data distribution may change over time, making the model obsolete.
Human / Organizational | Insufficient expertise | You may lack skills (statistics, ML, domain knowledge) required.
| Communication / stakeholder mismatch | Misunderstanding the goals with supervisors or domain experts.
| Motivation / burnout / time management | The workload may lead to fatigue or delays.
1️⃣ Themenwahl & Zieldefinition
Unklare oder zu breite Fragestellung | Das Thema ist zu vage oder umfasst zu viele Teilaspekte → keine klare Forschungsrichtung. | „Künstliche Intelligenz in der Medizin“ ohne Eingrenzung.
Themenänderung während der Arbeit | Änderungen im Projekt führen zu Verzögerungen. | Neue Methode scheint interessanter, Projekt wird umgeplant.
2️⃣ Zeitmanagement & Organisation
Zeitliche Fehleinschätzung | Einzelne Arbeitsschritte dauern deutlich länger als geplant. | Datenaufbereitung nimmt doppelt so viel Zeit wie erwartet.
Prokrastination / Motivationsabfall | Aufschieben oder Überforderung führt zu Zeitdruck am Ende. | Wochenlang kein Fortschritt, Abgabe in Gefahr.
Abgabefristen & Bürokratie übersehen | Formale Fristen (Anmeldung, Abgabe, Verlängerung) werden übersehen. | Anmeldung zu spät eingereicht.
3️⃣ Personelle Risiken
Ausfall von Projektteilnehmern (z. B. Krankheit) | Teammitglied oder Studierender selbst fällt temporär oder dauerhaft aus. | Krankheit oder familiäre Verpflichtungen.
Betreuer-Ausfall oder mangelnde Betreuung | Betreuer ist krank, wechselt Institution oder reagiert nicht. | Betreuer im Ausland, keine Rückmeldungen mehr.
4️⃣ Technische & Infrastruktur-Risiken
Hardwareausfall / Datenverlust | Rechnerdefekt, Festplattenfehler oder Stromausfall führen zu Verlust von Arbeit oder Daten. | Laptop kaputt, kein Backup.
Softwareprobleme / Versionskonflikte | Tools, Bibliotheken oder Updates führen zu Inkompatibilitäten. | Nach Update läuft Code nicht mehr.
Zugriffsverlust auf Systeme oder Server | Rechte oder Passwörter gehen verloren; Accounts gesperrt. | Uni-Account läuft ab.
5️⃣ Daten- & Forschungsrisiken
Datenqualität unzureichend | Fehlerhafte, unvollständige oder verrauschte Daten. | Messwerte fehlerhaft oder inkonsistent.
Fehlende Reproduzierbarkeit / Dokumentation | Arbeit kann später nicht nachvollzogen werden. | Keine Versionskontrolle, fehlende Protokolle.
6️⃣ Ethische & rechtliche Risiken
Datenschutzverletzung / ethische Probleme | Personenbezogene Daten oder vertrauliche Informationen unsachgemäß behandelt. | Veröffentlichung sensibler Patientendaten.
Plagiat / falsche Zitation | Unerlaubte Übernahme fremder Texte oder Ideen. | Copy-Paste aus Artikeln ohne Quellen.
Urheberrechtsverletzung | Nutzung von Bildern, Texten oder Code ohne Lizenz. | Grafiken aus Publikationen übernommen.
Interessenskonflikt mit externen Partnern | Externe Auftraggeber verlangen Ergebnismanipulation oder Geheimhaltung. | Firma will negative Resultate nicht veröffentlicht sehen.
7️⃣ Kommunikation & Zusammenarbeit
Schlechte Kommunikation mit Betreuer / Stakeholdern | Missverständnisse über Erwartungen oder Fortschritt. | Unterschiedliche Zielvorstellungen.
Mangelnde Abstimmung mit Kooperationspartnern | Externe Partner antworten zu spät oder gar nicht. | Unternehmen reagiert nicht auf E-Mails.
Fehlendes Feedback | Arbeit entwickelt sich in falsche Richtung. | Betreuer liest Entwurf erst kurz vor Abgabe.
8️⃣ Schreibprozess & Abgabe
Formatierungsprobleme / technische Fehler | LaTeX-Fehler, defekte Abbildungen, Verzeichnisse falsch. | Abbildungen nicht eingebunden.
Schreibblockaden / Überforderung am Ende | Zeitdruck, Angst, Stress → keine Produktivität. | Kurz vor Abgabe kein Fortschritt.
9️⃣ Externe & Umweltfaktoren
Krankheit / Unfall / persönliche Belastung | Unerwartete gesundheitliche Ausfälle. | Grippe, Unfall, familiäre Krise.
Pandemie / höhere Gewalt / Naturereignisse | Ereignisse außerhalb der Kontrolle stören den Zeitplan. | Laborzugang während Pandemie gesperrt.
Stromausfall / Internetprobleme | Technische Störungen verhindern Arbeit. | Kein Internetzugang während Online-Recherche.

## Tabelle3
1️⃣ Themenwahl & Zieldefinition
Scope & Planning | Scope creep / changing goals | The project expands beyond what is feasible in the available time.
| Underestimation of time / effort | Some tasks (data cleaning, debugging) often take much more time than expected.
Unklare oder zu breite Fragestellung | Das Thema ist zu vage oder umfasst zu viele Teilaspekte → keine klare Forschungsrichtung. | „Künstliche Intelligenz in der Medizin“ ohne Eingrenzung.
Unklare Ziele | Ziele sind zu schwammig formuliert. Ziele sind nicht messbar
Themenänderung während der Arbeit | Änderungen im Projekt führen zu Verzögerungen. | Neue Methode scheint interessanter, Projekt wird umgeplant.
2️⃣ Zeitmanagement & Organisation
Validation & Deployment | No real-world validation | The model might perform well in lab but fail in deployment.
Human / Organizational | Insufficient expertise | You may lack skills (statistics, ML, domain knowledge) required.
| Communication / stakeholder mismatch | Misunderstanding the goals with supervisors or domain experts.
| Motivation / burnout / time management | The workload may lead to fatigue or delays.
Zeitliche Fehleinschätzung | Einzelne Arbeitsschritte dauern deutlich länger als geplant. | Datenaufbereitung nimmt doppelt so viel Zeit wie erwartet.
Prokrastination / Motivationsabfall | Aufschieben oder Überforderung führt zu Zeitdruck am Ende. | Wochenlang kein Fortschritt, Abgabe in Gefahr.
Abgabefristen & Bürokratie übersehen | Formale Fristen (Anmeldung, Abgabe, Verlängerung) werden übersehen. | Anmeldung zu spät eingereicht.
3️⃣ Personelle Risiken
Ausfall von Projektteilnehmern (z. B. Krankheit) | Teammitglied oder Studierender selbst fällt temporär oder dauerhaft aus. | Krankheit oder familiäre Verpflichtungen.
Betreuer-Ausfall oder mangelnde Betreuung | Betreuer ist krank, wechselt Institution oder reagiert nicht. | Betreuer im Ausland, keine Rückmeldungen mehr.
4️⃣ Technische & Infrastruktur-Risiken
Technical / Infrastructure | Software / library dependencies / version conflicts | Upgrades or mismatches may break your code.
| Hardware failures / data loss | Disk crashes, hardware errors, power outages.
Hardwareausfall / Datenverlust | Rechnerdefekt, Festplattenfehler oder Stromausfall führen zu Verlust von Arbeit oder Daten. | Laptop kaputt, kein Backup.
Softwareprobleme / Versionskonflikte | Tools, Bibliotheken oder Updates führen zu Inkompatibilitäten. | Nach Update läuft Code nicht mehr.
Formatierungsprobleme / technische Fehler | LaTeX-Fehler, defekte Abbildungen, Verzeichnisse falsch. | Abbildungen nicht eingebunden.
5️⃣ Daten- & Forschungsrisiken
Data-related | Poor data quality / missing values / noise | Data may contain errors, missing or inconsistent entries, outliers, etc.
Data-related | Bias in data (sampling bias, measurement bias) | The data might systematically misrepresent some groups or features, harming generalizability.
Datenqualität unzureichend | Fehlerhafte, unvollständige oder verrauschte Daten. | Messwerte fehlerhaft oder inkonsistent.
Fehlende Reproduzierbarkeit / Dokumentation | Arbeit kann später nicht nachvollzogen werden. | Keine Versionskontrolle, fehlende Protokolle.
6️⃣ Ethische & rechtliche Risiken
Plagiat / falsche Zitation | Unerlaubte Übernahme fremder Texte oder Ideen. | Copy-Paste aus Artikeln ohne Quellen.
Urheberrechtsverletzung | Nutzung von Bildern, Texten oder Code ohne Lizenz. | Grafiken aus Publikationen übernommen.
7️⃣ Kommunikation & Zusammenarbeit
Schlechte Kommunikation mit Betreuer / Stakeholdern | Missverständnisse über Erwartungen oder Fortschritt. | Unterschiedliche Zielvorstellungen.
Mangelnde Abstimmung mit Kooperationspartnern | Externe Partner antworten zu spät oder gar nicht. | Unternehmen reagiert nicht auf E-Mails.
9️⃣ Externe & Umweltfaktoren
Krankheit / Unfall / persönliche Belastung | Unerwartete gesundheitliche Ausfälle. | Grippe, Unfall, familiäre Krise.
Pandemie / höhere Gewalt / Naturereignisse | Ereignisse außerhalb der Kontrolle stören den Zeitplan. | Laborzugang während Pandemie gesperrt.
Stromausfall / Internetprobleme | Technische Störungen verhindern Arbeit. | Kein Internetzugang während Online-Recherche.

## Table with Risks and Measures
Number | Group | Risk | Risk Description | Likelyhood | Severity | Likelyhood times Severity | Accept | Reduce | Transfer | Avoid | Detail Action | Strategy Decision What | When | Checkup When | Checkup Action or OK
1 | Goal | Unclear question | The topic description is to vague or contains to many goals | 2 | 2 | 4 |  | X |  |  | Define SMART goals | In the research section smart goals have been setup | 2099-10-23
2 | Goal | Unclear goals | The goals are not clearly defined or can not be measured | 2 | 3 | 6 |  | X |  |  | Describe which goals are part of scope | The introduction describes which parts of the initial project description are part of this document
3 | Time and Organisation | Insufficient expertise | Not knowing required tools or programming languages | 4 | 2 | 8 | X |  |  |  | Risk is accepted, learning is wanted effect | Accept : Nothing done | 2025-10-23
4 | Time and Organisation | Undererstimated time/effort | Some tasks take more time than initially expected | 4 | 3 | 12 | X |  |  |  | Document end of tasks in Miro Calendar, Reevaluate after project | Accept : Nothing done | 2025-10-23
5 | Time and Organisation | Other study projects | Other classes demand more attention, less time for project | 3 | 3 | 9 | X |  |  |  | Use minimum time for Projects/classes | Accept : Nothing done | 2025-10-23
6 | Time and Organisation | Work projects | Other projects at work demand urgent attention, less time for project | 4 | 3 | 12 |  | X |  |  | Reduction of risk due to starting early, defining blockers for study work | Added blockers in Work calendar, Work Account invited to meeting Series (Jour Fixe), Study Account: Set Blockers on Weekend, Researched with ChatGPT for optimal or minimal study plan | 2025-10-10
7 | Time and Organisation | Procrastination | Tasks are pushed back | 3 | 2 | 6 |  | X |  |  | Start early | Work on he project started 25.09.2025, when attending data quality meeting at AWS, beeing part of AWS Modernisation initiative | 2025-10-17
8 | Human Resources | Unavailability of main project staff, e.g. due to illness | One or multiple project staff are not available | 4 | 4 | 16 |  | X |  |  | Provide contact of partner working at BFH, Document in case it hapens | Contact of partner provided in teams, and added to Miro board | 2025-10-23
9 | Human Resources | Unavailability of advisor, e.g. due to illness, accident etc. | The advisor is not available | 3 | 4 | 12 |  |  | X |  | Advisor to define emergency replacement | Asked for Contact, Confirmed to be Jürgen Vogel | 2025-10-23
10 | Tech and Infrastructure | Software Version/Library/Dependency | Missmatch in Versions, new library versions break the code | 4 | 3 | 12 | X |  |  |  | Run the code multiple times, have tetcases e.g. unittests | Accept : Nothing done | 2025-10-23
11 | Tech and Infrastructure | Hardware is damaged | The Laptops or other material is damaged and needs repairs or replacement | 2 | 5 | 10 |  | X |  |  | Second Laptop, Code on Github/Miro/Teams/Outlook | Second Laptop is available at home, The Latex document is a Github project, documentation is on miro. Work Laptop can also be used for most tasks, but has no Latex installed | 23.10.205
12 | Data and research | Data related | Bias in data, not enough data | 4 | 3 | 12 | X |  |  |  | No preparation to be planned | Accept : Nothing done | 2025-10-23
13 | Data and research | Not reproducable work | The work provided can not be reproduced | 2 | 5 | 10 |  | X |  |  | Document bigger Steps, Upload Versions on Github of document, in Miro use Kanban to document tasks | Github project for Latex Document | 2025-10-10
14 | Ethical and Legal | Plagiarism or wrong citation | Unallowed or undeclared usage of sources | 2 | 5 | 10 |  | X |  |  | Use Citation, Bibliography | Jabref used as GUI for Biblliography, Biber used for build | 2025-10-17
15 | Ethical and Legal | Copyright | Used literature or materials which are restricted | 1 | 5 | 5 | X |  |  |  | Declare sources in bibliography, in case of post sources only use public documents | Accept : Nothing done | 2025-10-10
16 | Communication and Cooperation | Bad communication with stakeholder or advisor | Advisor or stakeholders are not heared. Their inputs are ignored | 2 | 4 | 8 |  | X |  |  | Weekly Advisor Meetings, Jour Fixe | Jour Fixe Setup | 2025-09-26
17 | Communication and Cooperation | insufficient exchange with external partners | External partners do not react, are delayed or communication towards them is late or poor | 1 | 5 | 5 |  | X |  |  | Stakeholders in Scrum Team | Keep exchange chanells also when changing team | 2025-09-26
18 | Force Majeure | Unforseen familiar crisis | Unecpected crisis in family | 2 | 5 | 10 | X |  |  |  | To be documented in miro calendar case it happens | Accept : Nothing done | 2025-10-23
19 | Force Majeure | General force majeure | Events which can not be influenced are very rare and very disruptive | 1 | 5 | 5 | X |  |  |  | To be documented in miro calendar case it happens | Accept : Nothing done | 2025-10-23

## Graphical Overview
[7 empty] | Number | Likelyhood | Severity
Likelyhood | Risk Matrix | Severity |  |  |  |  | 1 | 2 | 2
|  | Insignificant | Minor | Moderate | Major | Severe | 2 | 2 | 3
| Almost Certain | 15, 17, 19 | 11, 14 | 20 |  |  | 3 | 4 | 2
| Likely | 21 | 16 | 9 | 8 |  | 4 | 4 | 3
| Possible |  |  | 5 | 4, 6, 10, 12 |  | 5 | 3 | 3
| Unlikely |  | 1 | 2, 7 | 3 |  | 6 | 4 | 3
| Rare | [5 empty] | 7 | 3 | 2
[7 empty] | 8 | 4 | 4
[7 empty] | 9 | 3 | 4
[7 empty] | 10 | 4 | 3
[7 empty] | 11 | 2 | 5
[7 empty] | 12 | 4 | 3
[7 empty] | 13 | 2 | 5
[7 empty] | 14 | 2 | 5
[7 empty] | 15 | 1 | 5
[7 empty] | 16 | 2 | 4
[7 empty] | 17 | 1 | 5
[7 empty] | 18 | 2 | 5
[7 empty] | 19 | 2 | 5
[7 empty] | 20 | 1 | 5
[7 empty] | 21 | 1 | 4

## RiskEval
Number | Group | Risk | Likelyhood | Severity
1 | Goal | Unclear question | 2 | 2
2 | Goal | Unclear goals | 2 | 3
3 | Time and Organisation | Insufficient expertise | 4 | 2
4 | Time and Organisation | Undererstimated time/effort | 4 | 3
5 | Time and Organisation | Other study projects | 3 | 3
6 | Time and Organisation | Work projects | 4 | 3
7 | Time and Organisation | Procrastination | 3 | 2
8 | Human Resources | Unavailability of main project staff, e.g. due to illness | 4 | 4
9 | Human Resources | Unavailability of advisor, e.g. due to illness, accident etc. | 3 | 4
10 | Tech and Infrastructure | Software Version/Library/Dependency | 4 | 3
11 | Tech and Infrastructure | Hardware is damaged | 2 | 5
12 | Data and research | Data related | 4 | 3
13 | Data and research | Not reproducable work | 2 | 5
14 | Ethical and Legal | Plagiarism or wrong citation | 2 | 5
15 | Ethical and Legal | Copyright | 1 | 5
16 | Communication and Cooperation | Bad communication with stakeholder or advisor | 2 | 4
17 | Communication and Cooperation | insufficient exchange with external partners | 1 | 5
18 | Force Majeure | Unforseen familiar crisis | 2 | 5
19 | Force Majeure | General Force majeure | 2 | 5

## RiskTreatment
Number | Risk | Risk Description | Treatment | Treatment Description
1 | Unclear question | The topic description is to vague or contains to many goals | Reduce | Define SMART goals
2 | Unclear goals | The goals are not clearly defined or can not be measured | Reduce | Describe which goals are part of scope
3 | Insufficient expertise | Not knowing required tools or programming languages | Accept | Document after risk occured
4 | Undererstimated time/effort | Some tasks take more time than initially expected | Accept | Document end of tasks in Miro Calendar, Reevaluate after project
5 | Other study projects | Other classes demand more attention, less time for project | Accept | Use minimum time for Projects/classes
6 | Work projects | Other projects at work demand urgent attention, less time for project | Reduce | Reduction of risk due to starting early, defining blockers for study work
7 | Procrastination | Tasks are pushed back | Reduce | Start early
8 | Unavailability of main project staff | One or multiple project staff are not available | Accept | Document in case it hapens
9 | Unavailability of advisor | The advisor is not available | Transfer | Advisor to define emergency replacement
10 | Software Version/Library/Dependency | Missmatch in Versions, new library versions break the code | Accept | Run the code multiple times, have tetcases e.g. unittests
11 | Hardware is damaged | The Laptops or other material is damaged and needs repairs or replacement | Reduce | Second Laptop, Code on Github/Miro/Teams/Outlook
12 | Data related | Bias in data, not enough data | Accept
13 | Not reproducable work | The work provided can not be reproduced | Reduce | Document Steps, Upload Versions on Github
14 | Plagiarism or wrong citation | Unallowed or undeclared usage of sources | Reduce | Use Citation, Bibliography
15 | Copyright | Used literature or materials which are restricted | Accept
16 | Bad communication with stakeholder or advisor | Advisor or stakeholders are not heared. Their inputs are ignored | Reduce | Weekly Advisor Meetings
17 | insufficient exchange with external partners | External partners do not react, are delayed or communication towards them is late or poor | Reduce | Stakeholders in Scrum Team
18 | Unforseen familiar crisis | Unecpected crisis in family | Accept | To be documented in miro calendar case it happens
19 | General Force majeure | Events which can not be influenced are very rare and very disruptive | Accept | To be documented in miro calendar case it happens

## RiskWhatWhen
Number | Risk | Strategy Decision What | When
1 | Unclear question | In the research section smart goals have been setup | 2099-10-23
2 | Unclear goals | The introduction describes which parts of the initial project description are part of this document
3 | Insufficient expertise | Accept : Nothing done | 2025-10-23
4 | Undererstimated time/effort | Accept : Nothing done | 2025-10-23
5 | Other study projects | Accept : Nothing done | 2025-10-23
6 | Work projects | Added blockers in Work calendar, Work Account invited to meeting Series (Jour Fixe), Study Account: Set Blockers on Weekend, Researched with ChatGPT for optimal or minimal study plan | 2025-10-10
7 | Procrastination | Work on he project started 25.09.2025, when attending data quality meeting at AWS, beeing part of AWS Modernisation initiative | 2025-10-17
8 | Unavailability of main project staff, e.g. due to illness | Contact of partner provided in teams, and added to Miro board | 2025-10-23
9 | Unavailability of advisor, e.g. due to illness, accident etc. | Asked for Contact, Confirmed to be Jürgen Vogel | 2025-10-23
10 | Software Version/Library/Dependency | Accept : Nothing done | 2025-10-23
11 | Hardware is damaged | Second Laptop is available at home, The Latex document is a Github project, documentation is on miro. Work Laptop can also be used for most tasks, but has no Latex installed | 23.10.205
12 | Data related | Accept : Nothing done | 2025-10-23
13 | Not reproducable work | Github project for Latex Document | 2025-10-10
14 | Plagiarism or wrong citation | Jabref used as GUI for Biblliography, Biber used for build | 2025-10-17
15 | Copyright | Accept : Nothing done | 2025-10-10
16 | Bad communication with stakeholder or advisor | Jour Fixe Setup | 2025-09-26
17 | insufficient exchange with external partners | Keep exchange chanells also when changing team | 2025-09-26
18 | Unforseen familiar crisis | Accept : Nothing done | 2025-10-23
19 | General Force majeure | Accept : Nothing done | 2025-10-23

## CheckJuly24072026
Number | Risk | Occured, Yes/No | Detail | Why | Measures taken | Measure date
1 | Unclear question | No |  | Measures taken
2 | Unclear goals | No |  | Team Members, PO in team
3 | Insufficient expertise | Yes | Latex usage to change document structure | Some parts of the used bfh template had to be changed, some were changed due to amendments with tables etc. added and needed fixes | used chatgpt for review and changes | 2026-07-24
4 | Undererstimated time/effort | Yes | Efforts for writing were not commitable before holiday | Took to much time in relation to needed cool down times | Moved writing partially to holiday | 2026-07-24
5 | Other study projects | Yes | No time invested | Focus on this project |  | 2026-07-24
6 | Work projects | No | In December much more work on the project was possible, no incidents | Full focus on new topics
7 | Procrastination | No |  | Now time to finish | Working hard during beach holiday | 2026-07-24
8 | Unavailability of main project staff, e.g. due to illness | No
9 | Unavailability of advisor, e.g. due to illness, accident etc. | No
10 | Software Version/Library/Dependency | No
11 | Hardware is damaged | No
12 | Data related | No
13 | Not reproducable work | No
14 | Plagiarism or wrong citation | No
15 | Copyright | No
16 | Bad communication with stakeholder or advisor | No
17 | insufficient exchange with external partners | No
18 | Unforseen familiar crisis | No
19 | General force majeure | No
20 | Unknown Process | Yes | Finally after a lot of back and forth the invoice was handled trough sending it via post mail | BFH could not sign the new Terms of Post | Next invoice to be sent by mail directly | 2026-07-01

## CheckJanuary09
Number | Risk | Occured, Yes/No | Detail | Why | Measures taken | Measure date
1 | Unclear question | No |  | Measures taken
2 | Unclear goals | No |  | Team Members, PO in team
3 | Insufficient expertise | Yes | Latex usage to change document structure | Some parts of the used bfh template had to be changed, some were changed due to amendments with tables etc. added and needed fixes | used chatgpt for review and changes | 2026-01-04
4 | Undererstimated time/effort | Yes | Efforts for writing estimated lower, over 90 hours in holidays | Efforts to create new chapters was high, one chapter had to be rewritten | Removed some old chapter structure, finishing on weekend 10.01.2025 | 2026-01-02
5 | Other study projects | Yes | No time invested | Focus on this project |  | 2025-12-19
6 | Work projects | No | In December much more work on the project was possible, no incidents | Full focus on new topics
7 | Procrastination | No |  | Now time to finish | Work hard, some time off taken to work on projects | 2026-01-07
8 | Unavailability of main project staff, e.g. due to illness | No
9 | Unavailability of advisor, e.g. due to illness, accident etc. | No
10 | Software Version/Library/Dependency | No
11 | Hardware is damaged | No
12 | Data related | No
13 | Not reproducable work | No
14 | Plagiarism or wrong citation | No
15 | Copyright | No
16 | Bad communication with stakeholder or advisor | No
17 | insufficient exchange with external partners | No
18 | Unforseen familiar crisis | No
19 | General force majeure | No
20 | Unknown Process | Yes | Have to print the agreement and sign by Swiss Post | Agreement needs signature before handin | Has to be handled by author | 2026-01-05

## CheckDecember12
Number | Risk | Occured, Yes/No | Detail | Why | Measures taken | Measure date
1 | Unclear question | No |  | Measures taken
2 | Unclear goals | No |  | Team Members, PO in team
3 | Insufficient expertise | Yes | Issues at understanding pySpark code | Unknown programming language | Asked DQM team fo review of code. Discussed next steps | 2025-12-10
4 | Undererstimated time/effort | Yes | Expected to implement one automation PoC in Project 1 | Efforts required to restructure checks and implement environment, using pySpark needs more time | Moved implementation of code to Project 2, confirmed in Jour Fixe with Advisor | 2025-12-10
5 | Other study projects | Yes | Reviewing takes time | retaken 2 classes | Split of time | 2025-12-12
6 | Work projects | Yes | Workload better | First half since November more efforts still required, then able to swap and use more time for project 1 | Focus first on work projects then study related | 2025-12-12
7 | Procrastination | Yes | Postponing working on things | Reality | Learning on some evenings | 2025-12-12
8 | Unavailability of main project staff, e.g. due to illness | No
9 | Unavailability of advisor, e.g. due to illness, accident etc. | No
10 | Software Version/Library/Dependency | No
11 | Hardware is damaged | No
12 | Data related | No
13 | Not reproducable work | No
14 | Plagiarism or wrong citation | No
15 | Copyright | No
16 | Bad communication with stakeholder or advisor | No
17 | insufficient exchange with external partners | No
18 | Unforseen familiar crisis | No
19 | General force majeure | No
20 | Unknown Process | Yes | The process and requirements to get a MSE agreement for project work was not known. Resulted in many meetings between project team and BFH and Swiss Post | Knowledge of handling not available. Conflicting information such as not required 1'500 CHF passed. | Document the part in project document separately if time allows | 2025-12-10

## CheckNovember14
Number | Risk | Occured, Yes/No | Detail | Why | Measures taken | Measure date
1 | Unclear question | No |  | Measures taken
2 | Unclear goals | No |  | Team Members, PO in team
3 | Insufficient expertise | Yes | At usage of SAC and DSP | Unknown tools | Asked team for help, recieved help | 2025-11-10
4 | Undererstimated time/effort | No
5 | Other study projects | Yes | Reviewing takes time | retaken 2 classes | Split of time | 2025-10-11
6 | Work projects | Yes | Efforts and Incidents | less than 50% of ecpected time available for study project | None
7 | Procrastination | Yes | Postponing working on things | Reality | Learning on some evenings | 2025-10-19
8 | Unavailability of main project staff, e.g. due to illness | No
9 | Unavailability of advisor, e.g. due to illness, accident etc. | No
10 | Software Version/Library/Dependency | No
11 | Hardware is damaged | No
12 | Data related | No
13 | Not reproducable work | No
14 | Plagiarism or wrong citation | No
15 | Copyright | No
16 | Bad communication with stakeholder or advisor | No
17 | insufficient exchange with external partners | No
18 | Unforseen familiar crisis | No
19 | General force majeure | No