## Tabelle1
Date | Type | Hours | Action | Start | End
2026-09-18 | Home | 2 | first Meeting preparation and Meeting
2026-09-26 | Home | 2 | Setup of ChatgPT, confirm what i need to do after meeting 1 with expert
2026-09-27 | Home | 6 | Create first document, review and compare with samples using chatgpt
2026-10-03 | Home | 3.25 | Work on first document, refine phases and milestones | 9:20 | 13:10 | Weniger ca 45 Min
2026-10-03 | Home | 1 | Work on initial Thesis Document version, create the new document and remove outdated content of P1 and P2 | 13:50 | 14:50
2026-10-03 | Home | 1 | Restructure Document, remove chapters which are not part of Master Thesis | 21:15 | 22:15
2026-10-04 | Home | 2 | Restructure Document, add Chapters and add Todo Tags , Sweeping Miroboard, Tasks for Monday | 9:00 | 11:10
2026-10-10 | Home | 2 | Work on Introduction, rework when to state that it is 3 projects , Rework the descriptive Document
2026-10-11 | Home | 2 | Work on Introduction, write part for 3 staged work
2026-10-17 | Home | 5 | Work on Introduction, then continue on Project management, adding the updates since project 2
2026-10-18 | Home | 3 | Project Management
2026-10-18 | Home | 2.5 | Write the Use case
2026-10-22 | Home | 0.5 | Write on Effort Planning and Review
2026-10-22 | Home | 0.25 | Review what the content of Effort Planning and Review should be
2026-10-23 | Home | 0.5 | Write on Effort Planning and Review
2026-10-23 | Home | 1.5 | Miro Setup regarding dates, setup of Milestones timelines in excel to get phases efforts
2026-10-24 | Home | 2 | Start the Phases calculation,
2026-10-24 | Home | 1 | Continue on Phases calculation, includes relative %, but also number of hours per week and expected effort, however expected hours are not used | 11:55
2026-10-24 | Home | 1.5 | Risk Management review start | 20:45 | 22:15
2026-10-25 | Home | 3.5 | Work on Risk Management Update | 8:55 | 12:30